# Project Management Plan AAI-590 Group 6

Project: Machine Learning–Driven Covered Call Optimization

# Team Members

Christopher Mendoza

Fatimat Atanda

Carlos Ortiz

Swathi Pabbathi

# Project Duration

7 Weeks

# Estimated Effort

15 hours per team member per week (as recommended in the capstone guidelines)  ￼

# Timeline and Task Assignments

## Week 1 — Project Scope and Dataset Selection

Dates: Feb 22-28, 2026

Tasks

•	Finalize project scope and research question

•	Confirm ticker universe provided by Validex

•	Define strike and maturity bucket structure

•	Define modeling objective and evaluation metrics

•	Draft Introduction section of report

•	Establish GitHub repository and project structure

Assigned Team Members

Primary contributors:

•	Christopher Mendoza

•	Fatimat Atanda

Support contributors:

•	Carlos Ortiz

•	Swathi Pabbathi

Code/Writing Review

Reviewers:

•	Carlos Ortiz

•	Swathi Pabbathi

Review tasks:

•	Validate project scope

•	Review introduction draft

•	Confirm feasibility within 7-week timeline

## Week 2 — Project Architecture and Pipeline Design

Dates: March 1-7, 2026

Tasks

•	Design machine learning pipeline architecture

•	Define feature engineering plan

•	Define dataset schema and feature list

•	Design label construction methodology

•	Create pipeline diagram

•	Complete Project Management Plan submission

Assigned Team Members

Primary contributors:

•	Christopher Mendoza

•	Swathi Pabbathi

Support contributors:

•	Carlos Ortiz

•	Fatimat Atanda

Code/Writing Review

Reviewers:

•	Christopher Mendoza

•	Fatimat Atanda

Review tasks:

•	Validate pipeline design

•	Ensure architecture supports neural network training

•	Review project management plan document

## Week 3 — Data Cleaning and Exploratory Data Analysis

Dates: March 8-14,2026

Tasks

•	Implement Alpha Vantage data ingestion scripts

•	Align price data with quarterly fundamentals

•	Handle missing data and outliers

•	Generate exploratory visualizations

•	Produce dataset summary for report

Assigned Team Members

Primary contributors:

•	Christopher Mendoza

•	Swathi Pabbathi

Support contributors:

•	Carlos Ortiz

•	Fatimat Atanda

Code/Writing Review

Reviewers:

•	Carlos Ortiz

•	Fatimat Atanda

Review tasks:

•	Validate data pipeline integrity

•	Confirm dataset quality

•	Review exploratory analysis documentation

## Week 4 — Feature Engineering and Label Construction

Dates: March 15-21

Tasks

•	Compute valuation ratios

•	Compute volatility and momentum indicators

•	Construct payoff labels for classification target

•	Build final modeling dataset

•	Draft Background / Literature Review section

Assigned Team Members

Primary contributors:

•	Fatimat Atanda

•	Carlos Ortiz

Support contributors:

•	Christopher Mendoza

•	Swathi Pabbathi

Code/Writing Review

Reviewers:

•	Christopher Mendoza

•	Swathi Pabbathi

Review tasks:

•	Validate feature engineering logic

•	Confirm label construction methodology

•	Review background section draft

## Week 5 — Model Development and Initial Training

Dates: March 22-28

Tasks

•	Train baseline model (Random Forest)

•	Train neural network model (MLP)

•	Begin model validation and hyperparameter tuning

•	Draft Methods section of report

Assigned Team Members

Primary contributors:

•	Swathi Pabbathi

•	Christopher Mendoza

Support contributors:

•	Fatimat Atanda

•	Carlos Ortiz

Code/Writing Review

Reviewers:

•	Fatimat Atanda

•	Carlos Ortiz

Review tasks:

•	Validate training code

•	Verify model architecture

•	Review methodology description

## Week 6 — Model Evaluation and Backtesting

Dates: March 22-28, 2026

Tasks

•	Perform out-of-sample testing

•	Run strategy backtesting simulation

•	Evaluate model performance metrics

•	Generate performance visualizations

•	Begin drafting Results section

Assigned Team Members

Primary contributors:

•	Carlos Ortiz

•	Fatimat Atanda

Support contributors:

•	Christopher Mendoza

•	Swathi Pabbathi

Code/Writing Review

Reviewers:

•	Christopher Mendoza

•	Swathi Pabbathi

Review tasks:

•	Verify backtest results

•	Confirm evaluation methodology

•	Review results section draft

## Week 7 — Final Report, GitHub Repository, and Presentation

Dates: March 29 - April 4, 2026

Tasks

•	Finalize written report

•	Clean and document GitHub repository

•	Create final visualizations

•	Record project presentation video

•	Submit final deliverables

Assigned Team Members

Primary contributors:

•	All team members

Presentation speaking roles:

•	Christopher Mendoza

•	Fatimat Atanda

•	Carlos Ortiz

•	Swathi Pabbathi

Code/Writing Review

Final reviewers:

•	Entire team

Review tasks:

•	Verify final report structure

•	Ensure repository documentation is complete

•	Confirm presentation clarity and timing

# Presentation Recording Plan

Recording Window: Week 7

Steps

1.	Draft presentation slides

2.	Assign speaking sections

3.	Conduct internal rehearsal

4.	Record presentation video

5.	Upload and verify playback

Each team member will speak for approximately 2–3 minutes to ensure balanced participation.

# Collaboration and Version Control

The team will use GitHub for:

•	version control

•	code collaboration

•	documentation

•	reproducibility of experiments

The repository will include:

•	data ingestion scripts

•	feature engineering code

•	model training scripts

•	evaluation notebooks

•	documentation and README

This ensures compliance with the capstone requirement for a well-organized project code base.  ￼